## xtable
Variable | t0__Coefficient | t0__Significance | t1__Coefficient | t1__Significance | t2__Coefficient | t2__Significance | t3__Coefficient | t3__Significance
Annouced prematurely | 0.12781 | * | NA |  | 0.020923 |  | 0.11292 | *
Days pre-construction (log) | 0.044254 | *** | 0.11315 | *** | 0.08405 | * | -0.023565
State__Queensland | -0.12955 | ** | -0.065084 | * | 0.049285 |  | -0.16551 | ***
State__(small state) | -0.0046093 |  | 0.15416 |  | 0.15603 |  | -0.0095402
State__Victoria | -0.1856 | *** | -0.089068 | *** | -0.056424 |  | -0.19169 | ***
State__WA | -0.0646 |  | -0.022762 |  | 0.124 |  | -0.12426 | *
Sub-industry = Road | 0.045354 |  | -0.094827 |  | -0.037202 |  | 0.032396
Constructed post-GFC | -0.20974 | *** | -0.039418 |  | -0.17059 | *** | -0.13625 | **
Cost (real) when construction commenced | 0.057853 | *** | 0.067065 | *** | 0.030283 |  | 0.012081
Within 180 days of an election | -0.01865 |  | 0.36711 | * | -0.12284 | ** | 0.030287

## xtable_normal
Variable | t0__Coefficient | t0__Significance | t1__Coefficient | t1__Significance | t2__Coefficient | t2__Significance | t3__Coefficient | t3__Significance
(Intercept) | 0.066666 |  | -0.78065 | ** | -0.89631 | *** | 0.76305 | ***
premature_announcement | 0.14224 | * | NA |  | -0.12594 | * | 0.049936
log_Total_days_pre_construction | 0.0025851 |  | 0.0793 | * | 0.13033 | *** | -0.048312 | ***
big_statesQueensland | 0.044115 |  | -0.059962 |  | 0.054107 |  | 0.0098523
big_statesSmaller states | 0.088732 |  | 0.11576 |  | 0.05837 |  | 0.024244
big_statesVictoria | -0.047438 |  | -0.087554 |  | -0.032183 |  | 0.0038532
big_statesWestern Australia | 0.2296 | *** | 0.087464 |  | 0.26719 | *** | -0.027029
`Sub-industry`Road | 0.19018 | *** | 0.017195 |  | 0.073559 |  | 0.05633
Constructed_post_GFC | -0.024533 |  | 0.11639 |  | -0.052222 |  | -0.060717
log(First_cost_when_under_construction_real) | 0.030669 |  | 0.068246 | ** | 0.057556 | ** | -0.068845 | ***
election_180_days | 0.2265 | ** | 0.50303 | *** | -0.32306 | *** | 0.1741 | **

## Analysis
Logit model results | [9 empty] | Calculating the predicted probability of a cost overrun, pre and post GFC
| Full time period |  | t1 |  | t2 |  | t3 |  |  | Mean | Average Marginal Effects
| Coefficient | Significance | Coefficient | Significance | Coefficient | Significance | Coefficient | Significance | <-- Note: I had to double click the p-vals to get them to be recognised as numbers. If nothing looks significant, it's probably because the cells aren't being read successfully. |  | Across the full sample | If constructed pre GFC | If constructed post GFC
premature_announcement | 0.12781 | * | NA |  | 0.020923 |  | 0.11292 | * |  | 0.32472 | 0.041501 | 0.041501 | 0.041501
log_Total_days_pre_construction | 0.044254 | *** | 0.11315 | *** | 0.08405 | * | -0.023565 |  |  | 3.276 | 0.14497 | 0.14497 | 0.14497
big_statesQueensland | -0.12955 | ** | -0.065084 | * | 0.049285 |  | -0.16551 | *** |  | 0.24723 | -0.032029 | -0.032029 | -0.032029
big_statesSmaller states | -0.0046093 |  | 0.15416 |  | 0.15603 |  | -0.0095402 |  |  | 0.13838 | -0.00063782 | -0.00063782 | -0.00063782
big_statesVictoria | -0.1856 | *** | -0.089068 | *** | -0.056424 |  | -0.19169 | *** |  | 0.17712 | -0.032873 | -0.032873 | -0.032873
big_statesWestern Australia | -0.0646 |  | -0.022762 |  | 0.124 |  | -0.12426 | * |  | 0.15498 | -0.010012 | -0.010012 | -0.010012
`Sub-industry`Road | 0.045354 |  | -0.094827 |  | -0.037202 |  | 0.032396 |  |  | 0.77675 | 0.035229 | 0.035229 | 0.035229
Constructed_post_GFC | -0.20974 | *** | -0.039418 |  | -0.17059 | *** | -0.13625 | ** |  | 0.31365 | -0.065786 | 0 | -0.20974
log(First_cost_when_under_construction_real) | 0.057853 | *** | 0.067065 | *** | 0.030283 |  | 0.012081 |  |  | 4.5873 | 0.26539 | 0.26539 | 0.26539
election_180_days | -0.01865 |  | 0.36711 | * | -0.122836878781957 | ** | 0.030287 |  |  | 0.068266 | -0.0012732 | -0.0012732 | -0.0012732
[10 empty] | Predicted probabiliities | 0.34449 | 0.41027 | 0.20053
Log normal model results, project level
| Full time period |  | t1 |  | t2 |  | t3
| Coefficient | Significance | Coefficient | Significance | Coefficient | Significance | Coefficient | Significance
(Intercept) | 0.066666 |  | -0.78065 | ** | -0.89631 | *** | 0.76305 | ***
premature_announcement | 0.14224 | * | NA |  | -0.12594 | * | 0.049936
log_Total_days_pre_construction | 0.0025851 |  | 0.0793 | * | 0.13033 | *** | -0.048312 | ***
big_statesQueensland | 0.044115 |  | -0.059962 |  | 0.054107 |  | 0.0098523
big_statesSmaller states | 0.088732 |  | 0.11576 |  | 0.05837 |  | 0.024244
big_statesVictoria | -0.047438 |  | -0.087554 |  | -0.032183 |  | 0.0038532
big_statesWestern Australia | 0.2296 | *** | 0.087464 |  | 0.26719 | *** | -0.027029
`Sub-industry`Road | 0.19018 | *** | 0.017195 |  | 0.073559 |  | 0.05633
Constructed_post_GFC | -0.024533 |  | 0.11639 |  | -0.052222 |  | -0.060717
log(First_cost_when_under_construction_real) | 0.030669 |  | 0.068246 | ** | 0.057556 | ** | -0.068845 | ***
election_180_days | 0.2265 | ** | 0.50303 | *** | -0.32306 | *** | 0.1741 | **
Model specifications: logit model of the probability of a cost overrun occuring, log-normal model of the magnitude of cost overruns, if they occurred. Please see methodological appendix for details.
Interpretations:
Project attributes:
Mode (Sub-industry = road):
There is no difference in the probability of overruns between different modes.
Of the projects that experience overruns, road projects experienced higher overruns than rail projects on average during the pre-commitment and commitment - construction stages (the average difference between road and rail projects is 19%).
Project size (log(First cost when under construction)):
Note: Peter Wood suggests this should be interpreted as a proxy for project complexity.
Bigger projects were more likely to experience an overrun.
  Over the full time period, a 1% larger project budget was associated with a 6% higher probability of a cost overrun.
  Prior to the commitment stage, a 1% larger project budget was associated with a 7% higher probability of a cost overrun.
  Bigger projects were not more likely to experience a cost overrun in the later project stages.
Of the projects which experienced an overrun, project size had a mixed impact on the average size of overruns.
  A 1% larger project budget was associated with cost overruns that were 7% of initial project costs higher on average during the initial stage
  A 1% larger project budget was associated with cost overruns that were 6% of committed project costs higher on average during the committed – under construction stage.
  A 1% larger project budget was associated with cost overruns that were 7% of the first cost when under construction lower on average during the construction stage.
  This is in line with how we understand contingency funds to be used: added on to big projects’ budgets generously during the planning stages, but not always needed.
Process characteristics:
Premature initial cost announcement (defined as whether a project was possible or under consideration when the first cost estimate was announced) (Matching status numeric):
Note: this variable can’t be interpreted in relation to t1, because all the projects with costs in the possible and under consideration period had premature cost announcements.
Projects with premature initial cost announcements were 13% more likely to experience a cost overrun over the full period
  This risk is not confined to the early project stages. Rather, these projects are 11% more likely to experience a cost overrun during construction, but not specifically in any of the earlier periods.
Of the projects which experienced an overrun, projects with premature initial cost announcements also have larger cost overruns overall: 14% of the initial project cost higher than average.
  This is despite having lower overruns during the commitment – under construction stage (13% of the initial cost when committed lower than average). Presumably this result reflects that these projects are more rigorously assessed before granted the status of “committed”.
  (It’s worth interpreting this finding in light of the fact that these projects have a dramatically higher cost overrun in the t1 period than other projects, as we observe 0 cost overrun in this period in projects which did not have a premature initial cost announcement by definition)
Length of the planning process (log(Total days pre-construction)):
Projects with longer planning processes were more likely to experience an overrun.
  Over the full time period, cost overruns are 4% more likely for each 1% increase in the length of the planning process
  Between possible or under consideration and committed, cost overruns are 11% more likely for each 1% increase in the length of the planning process
  Between committed and under construction, cost overruns are 8% more likely for each 1% increase in the length of the planning process
  The length of the planning process does not change the probability of a cost overrun occurring during construction.
Of the projects which experienced an overrun, longer planning processes has mixed impacts on the average size of the overrun.
  Prior to commitment, a 1% increase in the length of the planning process was associated with a higher cost overrun (8% of initial project cost higher, on average).
  Between committed and under construction, a 1% increase in the length of the planning process was associated with a higher cost overrun (13% of the first cost when committed higher, on average).
  But during construction, a 1% increase in the length of the planning process was associated with a lower cost overrun (4% of the first cost when under construction lower, on average).
  This appears to be support with the “escalation” argument..
Constructed post-GFC:
Notes: the first draft of the report made a slight error in saying that the projects completed after the GFC were less likely to experience an overrun. It’s actually the projects for which construction started after the collapse of Lehman Brothers (so during or after the GFC) that performed better. I’ve included the variable in all the regressions so that the results are comparable. However, I think it’s important to focus on the results during construction (t3), because the GFC variable categorises projects on the timing of this third stage.
Projects constructed before the GFC were more likely to experience a cost overrun:
  Over the full time period, projects constructed before the GFC were 24% more likely to experience a cost overrun.
  Between commitment – construction, projects constructed before the GFC were 17% more likely to experience a cost overrun.
  During construction, projects constructed before the GFC were 13% more likely to experience a cost overrun ***
*** I think this third result is the one which should be reported, because our variable distinguishes projects on the timing of their construction.
Of the projects which experienced an overrun, projects constructed before the GFC experienced cost overruns of the same size, on average, as those constructed after that point.
Election:
Projects which were announced as election promises are 36% more likely to experience a cost overrun prior to a formal commitment being made.
However, they’re also 12% less likely to experience a cost overrun between the first proper funding commitment and construction.
Of those that experience a cost overrun, the average magnitude of cost overruns for election promises is higher than non-election promises:
  23% of initial project costs higher over the full time period
  50% of initial project costs higher before a final funding commitment is made
  18% of initial construction costs higher during the construction period
  But 32% of initial committed costs lower between the first funding commitment and the commencement of construction.
States:
Note that NSW is the base state. All conclusions should be interpreted relative to NSW.
The upshot is that QLD and VIC performed better than NSW, WA and the smaller states.
Queensland:
Has a lower probability of cost overruns than NSW projects, given the characteristics of its infrastructure projects.
QLD projects were:
  14% less likely to experience an overrun over the full time period than NSW projects
  6% less likely to experience an overrun prior to commitment than NSW projects
  17% less likely to experience an overrun during construction than NSW projects
Of the projects which experienced an overrun, the average size of cost overruns on QLD projects was no different from that of NSW’s projects.
Victoria:
Has a lower probability of cost overruns than NSW, given the characteristics of its infrastructure projects.
VIC projects were:
  20% less likely to experience an overrun over the full time period than NSW projects
  9% less likely to experience an overrun prior to commitment than NSW projects
  19% less likely to experience an overrun during construction than NSW projects
Of the projects which experienced an overrun, the average size of cost overruns on VIC projects was no different from that of NSW’s projects.
Western Australia:
Has a 12% lower probability of cost overruns than NSW during construction.
However, Of the projects which experienced an overrun, the average size of cost overruns on WA projects was larger than that of NSW’s projects. On average, they were:
  23% larger than NSW overall, as a percentage of the initial project cost
  26% larger than NSW between the funding commitment to the commencement of construction, as a percentage of the first funding commitment
  But no different from NSW prior to the first funding commitment, or during construction.
Other states:
…are no different on average from NSW.

## Logit all
V1 | dF/dx | Std. Err. | z | P>¦z¦ | P>¦z¦
premature_announcement | 0.12781 | 0.066492 | 1.9221 | 0.054591 | 0.054591 | *
log_Total_days_pre_construction | 0.044254 | 0.010566 | 4.1883 | 2.8106e-05 | 2.8106e-05 | *
big_statesQueensland | -0.12955 | 0.055384 | -2.3391 | 0.019329 | 0.019329
big_statesSmaller states | -0.0046093 | 0.065926 | -0.069916 | 0.94426 | 0.94426
big_statesVictoria | -0.1856 | 0.05302 | -3.5005 | 0.00046432 | 0.00046432
big_statesWestern Australia | -0.0646 | 0.065299 | -0.98929 | 0.32252 | 0.32252
`Sub-industry`Road | 0.045354 | 0.050035 | 0.90645 | 0.3647 | 0.3647
Constructed_post_GFC | -0.20974 | 0.043565 | -4.8145 | 1.4759e-06 | 1.4759e-06
log(First_cost_when_under_construction_real) | 0.057853 | 0.020428 | 2.832 | 0.0046255 | 0.0046255
election_180_days | -0.01865 | 0.082304 | -0.2266 | 0.82073 | 0.82073
Note on E1: Lucille Danks: Copied data
Note on F1: Lucille Danks: Raw data

## Logit t1
V1 | dF/dx | Std. Err. | z | P>¦z¦ | P>¦z¦
*
log_Total_days_pre_construction | 0.11315 | 0.030981 | 3.6524 | 0.00025978 | 0.00025978
big_statesQueensland | -0.065084 | 0.034273 | -1.899 | 0.057565 | 0.057565
big_statesSmaller states | 0.15416 | 0.12882 | 1.1967 | 0.23144 | 0.23144
big_statesVictoria | -0.089068 | 0.032832 | -2.7128 | 0.0066718 | 0.0066718
big_statesWestern Australia | -0.022762 | 0.048802 | -0.46641 | 0.64092 | 0.64092
`Sub-industry`Road | -0.094827 | 0.069095 | -1.3724 | 0.16993 | 0.16993
Constructed_post_GFC | -0.039418 | 0.035491 | -1.1106 | 0.26673 | 0.26673
log(First_cost_when_under_construction_real) | 0.067065 | 0.019715 | 3.4017 | 0.00066963 | 0.00066963
election_180_days | 0.36711 | 0.20177 | 1.8195 | 0.06884 | 0.06884
Note on E1: Lucille Danks: Hard copy of data
Note on F1: Lucille Danks: Raw data

## Logit t2
V1 | dF/dx | Std. Err. | z | P>¦z¦ | P>¦z¦
premature_announcement | 0.020923 | 0.0766715554045056 | 0.272887888219598 | 0.78494 | 0.78494
log_Total_days_pre_construction | 0.08405 | 0.0455836585594931 | 1.84387264477981 | 0.065202 | 0.065202
big_statesQueensland | 0.049285 | 0.0750161331955864 | 0.656996663315566 | 0.51118 | 0.51118
big_statesSmaller states | 0.15603 | 0.0956859597064635 | 1.63060431006641 | 0.10297 | 0.10297
big_statesVictoria | -0.056424 | 0.063308279964288 | -0.891259964444389 | 0.37279 | 0.37279
big_statesWestern Australia | 0.124 | 0.0913747986476119 | 1.35702913625043 | 0.17477 | 0.17477
`Sub-industry`Road | -0.037202 | 0.0585501122323163 | -0.635385501903409 | 0.52518 | 0.52518
Constructed_post_GFC | -0.17059 | 0.0424927554378003 | -4.01465222330068 | 5.9534e-05 | 5.9534e-05
log(First_cost_when_under_construction_real) | 0.030283 | 0.019633470984929 | 1.54241296856602 | 0.12297 | 0.12297
election_180_days | -0.122836878781957 | 0.0497002722412449 | -2.47155343909802 | 0.013453 | 0.013453
Note on E1: Lucille Danks: Hard coded
Note on F1: Lucille Danks: raw data

## Logit t3
V1 | dF/dx | Std. Err. | z | P>¦z¦ | P>¦z¦
premature_announcement | 0.11292 | 0.0648641517630304 | 1.74086221853455 | 0.081708 | 0.081708
log_Total_days_pre_construction | -0.023565 | 0.0271050071314177 | -0.869404462784217 | 0.38463 | 0.38463
big_statesQueensland | -0.16551 | 0.0603350581267343 | -2.74315537804433 | 0.0060852 | 0.0060852
big_statesSmaller states | -0.0095402 | 0.0804011640955076 | -0.118658029878675 | 0.90555 | 0.90555
big_statesVictoria | -0.19169 | 0.0611752681198462 | -3.13351221481522 | 0.0017273 | 0.0017273
big_statesWestern Australia | -0.12426 | 0.0698752518555981 | -1.77836211314676 | 0.075344 | 0.075344
`Sub-industry`Road | 0.032396 | 0.0658638305659534 | 0.491864106733453 | 0.62282 | 0.62282
Constructed_post_GFC | -0.13625 | 0.0585267955557126 | -2.32794065201112 | 0.019915 | 0.019915
log(First_cost_when_under_construction_real) | 0.012081 | 0.0231795956790457 | 0.521189034013969 | 0.60224 | 0.60224
election_180_days | 0.030287 | 0.0804414291739833 | 0.376505756582939 | 0.70654 | 0.70654
Note on E1: Lucille Danks: Hard coded
Note on F1: Lucille Danks: raw data

## lL project all
term | estimate | std.error | statistic | p.value
(Intercept) | 0.066666 | 0.14293 | 0.46643 | 0.6415
premature_announcement | 0.14224 | 0.079042 | 1.7995 | 0.073703
log_Total_days_pre_construction | 0.0025851 | 0.014449 | 0.17891 | 0.85822
big_statesQueensland | 0.044115 | 0.078581 | 0.5614 | 0.57526
big_statesSmaller states | 0.088732 | 0.087982 | 1.0085 | 0.31462
big_statesVictoria | -0.047438 | 0.094915 | -0.4998 | 0.61786
big_statesWestern Australia | 0.2296 | 0.086387 | 2.6578 | 0.0086123
`Sub-industry`Road | 0.19018 | 0.067247 | 2.8281 | 0.0052415
Constructed_post_GFC | -0.024533 | 0.070114 | -0.3499 | 0.72685
log(First_cost_when_under_construction_real) | 0.030669 | 0.024568 | 1.2484 | 0.21361
election_180_days | 0.2265 | 0.098658 | 2.2958 | 0.0229

## lL project t1
term | estimate | std.error | statistic | p.value
(Intercept) | -0.78065 | 0.31322 | -2.4924 | 0.014729
log_Total_days_pre_construction | 0.0793 | 0.046815 | 1.6939 | 0.094122
big_statesQueensland | -0.059962 | 0.1075 | -0.55779 | 0.57853
big_statesSmaller states | 0.11576 | 0.10964 | 1.0558 | 0.29419
big_statesVictoria | -0.087554 | 0.15015 | -0.58312 | 0.56143
big_statesWestern Australia | 0.087464 | 0.11638 | 0.75156 | 0.4545
`Sub-industry`Road | 0.017195 | 0.088206 | 0.19494 | 0.84593
Constructed_post_GFC | 0.11639 | 0.091061 | 1.2781 | 0.20485
log(First_cost_when_under_construction_real) | 0.068246 | 0.032865 | 2.0765 | 0.041016
election_180_days | 0.50303 | 0.11808 | 4.2602 | 5.4721e-05
0 | 0 | 0 | 0 | 0

## lL project t2
term | estimate | std.error | statistic | p.value
(Intercept) | -0.89631 | 0.18065 | -4.9616 | 2.13e-06
premature_announcement | -0.12594 | 0.07045 | -1.7877 | 0.076134
log_Total_days_pre_construction | 0.13033 | 0.029372 | 4.4372 | 1.9138e-05
big_statesQueensland | 0.054107 | 0.079962 | 0.67666 | 0.49981
big_statesSmaller states | 0.05837 | 0.078948 | 0.73935 | 0.46102
big_statesVictoria | -0.032183 | 0.087369 | -0.36835 | 0.71321
big_statesWestern Australia | 0.26719 | 0.082681 | 3.2315 | 0.0015574
`Sub-industry`Road | 0.073559 | 0.061186 | 1.2022 | 0.23145
Constructed_post_GFC | -0.052222 | 0.06675 | -0.78235 | 0.43542
log(First_cost_when_under_construction_real) | 0.057556 | 0.023676 | 2.431 | 0.01641
election_180_days | -0.32306 | 0.084582 | -3.8195 | 0.00020555

## lL project t3
row.names(as.data.frame.matrix(coeftest(fit_logistic_co_all_v4_t3, | Estimate | Std. Error | t value | Pr(>¦t¦)
(Intercept) | 0.76305 | 0.11448 | 6.6654 | 3.4857e-10
premature_announcement | 0.049936 | 0.063309 | 0.78876 | 0.43134
log_Total_days_pre_construction | -0.048312 | 0.011573 | -4.1745 | 4.7477e-05
big_statesQueensland | 0.0098523 | 0.062939 | 0.15654 | 0.87579
big_statesSmaller states | 0.024244 | 0.070469 | 0.34403 | 0.73125
big_statesVictoria | 0.0038532 | 0.076022 | 0.050686 | 0.95964
big_statesWestern Australia | -0.027029 | 0.069192 | -0.39064 | 0.69655
`Sub-industry`Road | 0.05633 | 0.053862 | 1.0458 | 0.29712
Constructed_post_GFC | -0.060717 | 0.056158 | -1.0812 | 0.28114
log(First_cost_when_under_construction_real) | -0.068845 | 0.019677 | -3.4987 | 0.00059605
election_180_days | 0.1741 | 0.07902 | 2.2033 | 0.028913

## Goodness of fit
Model | logLikelihood | AIC | BIC | R_sq | Adj_R_sq
Logit_all | -277.784 | 577.568 | 624.2539 | NA | NA
Loglogistic_project_level_all | -75.1179 | 174.2359 | 212.6839 | 0.164744427822671 | 0.115899072724581
Logit_t1 | -48.1227 | 116.2454 | 146.5497 | NA | NA
Loglogistic_project_level_t1 | -29.87 | 81.74 | 109.3594 | 0.319972044602515 | 0.244413382891683
Logit_t2 | -140.8109 | 303.6217 | 344.0283 | NA | NA
Loglogistic_project_level_t2 | -32.3833 | 88.7665 | 124.2364 | 0.330239585540253 | 0.279112836344852
Logit_t3 | -270.4497 | 562.8995 | 609.5853 | NA | NA
Loglogistic_project_level_t3 | -34.7226 | 93.4452 | 131.8933 | 0.232891688203935 | 0.188031553011182