## Slide 1
 | Risk minimisation |  | Risk measurement | Ongoing risk monitoring | 
 | Mitigate avoidable risks | Reduce estimation error | Measure the remaining risk | Account for risk in investment decisions | Manage risk throughout construction
C’wlth |  |  |  |  | 
NSW |  |  |  |  | 
VIC |  |  |  |  | 
QLD |  |  |  |  | 
WA |  |  |  |  | 
SA |  |  |  |  | 

## Slide 2
 | Commonwealth |  | NSW | VIC | QLD | WA | SA
Expected value |  |  |  |  |  |  | 
Sensitivity analysis |  |  |  |  |  |  | 
Probability pricing |  |  |  |  |  |  | 
Reference class forecasting |  |  |  |  |  |  | 

## Slide 3
Unavoidable risks
Avoidable and unavoidable risks
1
Underrun
Overrun

## Slide 4
Unavoidable risks
Reduction in estimation error
1
Underrun
Overrun

## Slide 5
50%
50%
Observed distribution
Assumed distribution
1
Underrun
Overrun
25%
34%
Notes: Chart 8
Title: Cost outcomes are less extreme across a portfolio of projects than on any individual project
Subtitle: Average probability distribution of final project costs as a proportion of initial project costs for individual projects and the aggregate probability distribution of Australia’s final transport infrastructure expenditure over 2000 – 2015 as a proportion of initial investment intentions, per cent
Notes: This figure is a graphical representation of the Linberg-Levy Central Limit Theorem as it relates to the management of cost overruns. As the sample of infrastructure projects increases, the variance of cost outcomes that could be observed, on average, across the portfolio of projects decreases, and the average cost outcome across the portfolio converges to the expected value of cost overruns for any individual project. For this reason, the individual project and portfolio level probability distributions share the same expected value, but the latter distribution has a smaller spread and is symmetrical. Both distributions share the same expected value.
This diagram is a stylized representation of the differences between project and portfolio level risks. Figure XX in appendix XX presents the raw data underpinning this comparison.
Source:

## Slide 6
Chart: 
| 1 | 3
Bottom of the Association for the Advancement of Cost Engineering International cost estimate classification matrix | 30 | 3
Top of the Association for the Advancement of Cost Engineering International cost estimate classification matrix | 70 | 12
Chart: 
Bottom of the two QLD series | 40 | 10
Top of the two QLD series | 30 | 10
Chart: 
Bottom of the SA ranges | 40 | 0
Top of the SA ranges | 30 | 40
Chart: 
Bottom of the NGTSM | 15 | 5
Top of NGTSM | 10 | 5
Association for the Advancement of Cost Engineering
South Australian Department of Planning, Transport and Infrastructure
QLD Department of Transport and Main Roads
National Guidelines for Transport System Management

## Slide 7
Chart: 
| Initial cost announcement | Budget commitment | Contract award | Completion of construction
Investment Monitor | 3520000000 | 8780000000 | 14106000000 | 14357000000
Grattan Dataset | 3664600000 | 6544400000 | 12741200000 | 14210600000
Investment Monitor dataset
Grattan dataset

## Slide 8
Chart: 
| Prior to a formal funding commitment | Budget commitment – under construction | During construction | Total
Series 2 | 8.857 | 15.2523
Series 1 | 8.857 | 6.3953 | 9.1434 | 24.3956
Error bars | 8.857 | 15.2523 | 24.3956
Chart: 
| Prior to a formal funding commitment | Budget commitment – under construction | During construction | Total
Series 2 | 6.4966 | 32.6504
Series 1 | 6.4966 | 26.1538 | 19.3166 | 51.967
Error bars | 6.4966 | 32.6504 | 51.967
Investment monitor dataset
Grattan dataset
Notes: This chart has been reviewed on 21/10/2016.
Title: A third of cost overruns occur prior to budget commitments
Subtitle: Cost overruns by project stage, per cent
Notes: Australian transport projects, completed between 2001 and 2015.
Source: Deloitte Investment Monitor dataset; Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Overall cost overruns

## Slide 9
50%
1
Underrun
Overrun
Expected value
P90
50%
40%
10%
Median = P50
Full distribution
Variance
Notes: This chart has been reviewed on 21/10/2016.
Title: Key risk measurement and management concepts
Subtitle: Illustrative probability distribution of cost outcomes on individual projects, per cent
Notes: The distribution of cost risks depicted is a stylized representation of the distribution of cost overruns observed in the Investment Monitor; see appendix xx for details. This graph’s illustrative purpose is to graphically present the relative distances between the median, 90th quantile and expected value of cost overruns.
Sources: Deloitte Investment Monitor, Grattan analysis

## Slide 10
50%
1
Underrun
Overrun
Notes: This chart has been reviewed on 21/10/2016.
Title: Key risk measurement and management concepts
Subtitle: Illustrative probability distribution of cost outcomes on individual projects, per cent
Notes: The distribution of cost risks depicted is a stylized representation of the distribution of cost overruns observed in the Investment Monitor; see appendix xx for details. This graph’s illustrative purpose is to graphically present the relative distances between the median, 90th quantile and expected value of cost overruns.
Sources: Deloitte Investment Monitor, Grattan analysis