## Slide 1: Charts for cost overruns on transport infrastructure projects report
October 2016

## Slide 2
Chart: 
| ≤ 25% | 0% | ≤ 25% | 25% - 50% | > 50%
Proportion of the value of overruns | -9.3807 | 0 | 6.376 | 4.261 | 98.7436
Chart: 
| ≤ 25% | 0% | ≤ 25% | 25% - 50% | > 50%
Proportion of projects | 9.2251 | 56.6421 | 11.2546 | 5.7196 | 17.1587
Cost underruns
On budget
Cost overruns
Frequency of cost overruns as a proportion of all projects, per cent
Value of cost overruns as a proportion of total cost overruns, per cent
Notes: This chart has been reviewed on 21/10/2016.
Title: Large cost overruns are uncommon, but expensive Subtitle: per cent
Notes: Australian transport projects completed between 2001 and 2015 Source: Deloitte Investment Monitor, Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Overall cost overruns

## Slide 3
Chart: 
| Victorian Auditor General 2010 | Duffield et al. 2008 | Wood 2010 | NSW Auditor General 2015 | Love et al. 2013 | Grattan Institute 2016
Sample size | 7 | 23 | 46 | 50 | 62 | 542
Column1
Notes: This chart has been reviewed on 21/10/2016.
Title: This report analyses upwards of nine times more Australian projects than previous studies
Subtitle: Sample sizes of previous studies into cost overruns on Australian transport infrastructure projects.
Sources: Cited studies and Deloitte Investment Monitor, Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Summary statistics

## Slide 4
First public cost announcement
Formal funding commitment
Commencement of construction
Project completion
Notes: This chart has been reviewed on 21/10/2016.
Title: Project stages

## Slide 5
Chart: 
| First public cost announcement | Formal funding commitment | Commencement of construction | Project completion
We know these overruns occur: | 0 | 8.857 | 15.2523 | 24.3956
It could be as high as this | 0 | 19.3567 | 31.9839 | 42.4547
Assuming no cost overrun
occurred where not
observed directly
Assuming the average rate of overrun where
not observed directly
Notes: This chart has been reviewed on 21/10/2016.
Title: Cost overruns are likely to be higher than reported
Subtitle: Average cost overrun rates as a proportion of initial costs, by project stage.
Notes: All cost overrun estimates contained elsewhere in this report have been estimated under the assumption that no overrun occurred where not observed directly, which is the illustrated by the lower bound illustrated in this graph. Australian transport projects completed between 2001 and 2015.
Source: Deloitte Investment Monitor dataset and Grattan dataset; Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Overall cost overruns

## Slide 6
11% directly attributable to scope changes
89% attributable to other causes
Chart: 
| Chunk for formatting | Scope changes | Other/unknown
Causes of cost overruns | 0.18 | 0.11359 | 0.70641
Notes: This chart has been reviewed on 21/10/2016.
Title: Most cost overruns are not attributable to substantive scope changes
Subtitle: Proportion of cost overruns attributable to scope changes, per cent
Notes: Based upon detailed investigation of 56 Australian transport infrastructure projects completed between 2008 and 2013, using publicly available data sources. The value of scope changes have been estimated where possible as the percentage of the total project cost (where scope changes were described as a percentage of project scope), or else by the total value of cost overruns incurred during the period the scope change took place.
Source: Grattan analysis.
Analysis in analysis tab of C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\Grattan dataset analysis\Analysis of the Grattan dataset 20160929

## Slide 7
Chart: 
| Percentage of projects | Percentage of the cost of cost overruns
Possible or under consideration | 32.4723 | 74.2976
Committed | 26.1993 | 6.5845
Under construction | 41.3284 | 19.1178
Projects with first cost
announced during
construction
Projects with first cost
announced alongside
a budget commitment
Projects with first cost
announced prior to a
budget commitment
Notes: This chart has been reviewed on 21/10/2016.
Title: The projects with early initial cost announced account for most of the value of cost overruns
Subtitle: Per cent
Notes: Australian transport projects completed between 2001 and 2015
Source: Deloitte Investment Monitor, Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM results\Summary statistics

## Slide 8
Chart: 
| Mean project size when possible or under consideration (assume zero overrun if not observed) | Mean project size when committed (assume zero overrun if not observed) | Mean project size when under construction (assume zero overrun if not observed) | Mean project size when completed (assume zero overrun if not observed)
Possible or under consideration | 225.6174 | 282.5844 | 311.7379 | 342.3009
Committed | 208.3205 | 208.3833 | 223.2769 | 221.1374
Under construction | 196.478 | 196.478 | 196.478 | 220.0686
First public
cost announcement
Formal budget
commitment
Commencement
of construction
Completed
Projects with first cost announced prior to a budget commitment
Projects with first cost
announced as a budget commitment,
prior to construction commencing
Projects with first cost
announced during construction
Notes: This chart has been reviewed on 21/10/2016.
Title: Projects announced earlier have larger percentage cost overruns at all stages of the project lifecycle
Subtitle: Average project size of each cohort, by project stage
Notes: Australian transport projects, completed between 2001 and 2015. Projects’ maturities at the time of initial cost announcements are inferred from each project’s stated maturity when the project entered the Deloitte Investment Monitor. Where initial cost announcements were very low profile, it is possible that the Deloitte Investment Monitor may have missed the announcement and erroneously recorded the first cost announcement as having occurred when the project reached a more mature stage. Given this data collection methodology, it should be noted late initial cost announcements may in fact reflect that earlier cost announcements were of a particularly low profile.
Source:Deloitte Investment Monitor, Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM results\Summary statistics

## Slide 9
Chart: 
| Coalition | Labor | Greens
IA projects | 14.5795 | 3.0051 | 0
IA initiatives | 59.8606 | 62.8677 | 53.9874
Not on IA | 25.5599 | 34.1272 | 46.0126
Not on IA list
On IA list as initiative only
On IA list
Notes: This chart has been reviewed on 21/10/2016.
Title: The vast majority of committed money from all 3 major parties is for projects not endorsed by Infrastructure Australia
Subtitle: Value of specific election commitments to transport infrastructure projects, $2016 billion
Notes: IIncludes projects where a specific dollar amount could be discerned from campaign material or, in the case of the coalition, from the 2016-17 budget papers. Excludes projects for which construction has already commenced.
Source: Liberal Party (2016); Australian Labor Party (2016); Australian Greens (2016); Treasury (2016); Treasury (2014); Infrastructure Australia (2016); Grattan analysis
Analysis in Dropbox (Grattan Institute)\Transport Program\Program wide research\20160517 Election promises.xlsx

## Slide 10
Chart: 
| Prior to a formal funding commitment | Budget commitment – under construction | During construction | Total
Series 2 | 8.857 | 15.2523
Series 1 | 8.857 | 6.3953 | 9.1434 | 24.3956
Error bars | 8.857 | 15.2523 | 24.3956
Notes: This chart has been reviewed on 21/10/2016.
Title: A third of cost overruns occur prior to budget commitments
Subtitle: Cost overruns by project stage, per cent
Notes: Australian transport projects, completed between 2001 and 2015.
Source: Deloitte Investment Monitor dataset; Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Overall cost overruns

## Slide 11
Few projects are cancelled once announced
Proportion of projects cancelled at each project stage
Chart: 
| Prior to a formal funding commitment | Budget commitment - under construction | During construction
Cancellation rate | 28.1476 | 14.834 | 13.6708
Notes: This chart has been reviewed on 21/10/2016.
Title: Few projects are cancelled once announced Subtitle: Percentage of projects cancelled at each project stage
Notes: Australian transport projects, planned or completed between 2001 and 2015.
Sources: Deloitte Investment Monitor dataset; Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Survival analysis

## Slide 12
Chart: 
| Assumed | Observed
Underrun | 25 | 9.2251
On budget | 50 | 56.6421
Overrun | 25 | 34.1328
Underruns
On
budget
Overruns
Underruns
On
budget
Overruns
Assumed prevalence
Observed prevalence
Notes: This chart has been reviewed on 21/10/2016.
Title: Experts systematically underestimate the likelihood of cost overruns
Subtitle: Assumed and observed probability distributions of cost overruns, per cent
Notes: The assumed prevalence of cost overruns is inferred from the common representation of cost risk as symmetrically distributed in cost estimation guidance, and the assumption that budget costs are P75 – P90 costs, which implies that no more than 25% of projects being expected to experience cost overruns.
Sources: Australian risk management guidelines referenced in appendix XX, and Deloitte Investment Monitor, Grattan analysis
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Summary statistics

## Slide 13
Chart: 
| Mean overrun
Less than 300m | 30.6122 | 23.1526
300m-600m | 46.6667 | 32.5255
Greater than 600m | 53.6585 | 54.1778
Prevalence of cost overruns
Magnitude of cost overruns
Notes: This chart has been reviewed on 21/10/2016.
Title: Cost overruns are more common and larger on average among big projects
Subtitle: Prevalence and average magnitude of cost overruns as a percentage of initial project costs by project size, per cent
Notes: Australian transport projects completed between 2001 and 2015. Project size is defined by project value at the commencement of construction.
Source: Deloitte Investment Monitor; Grattan analysis
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\IM Results\Overall cost overruns

## Slide 14
Chart: 
| Road | Rail | Road | Rail | Road | Rail
Series 1 | 0 | 19.6921 | 8.1099 | 0 | 9.6177 | 8.3803 | 0 | 29.3098 | 16.4902 | 0
First announced to contracted
Contracted to completed
Overall
Road
projects
Rail
projects
Notes: This chart has been reviewed on 21/10/2016.
Title: Both road and rail projects suffer from cost overruns, but at different stages
Subtitle: Average magnitude of cost overruns on Australian transport infrastructure projects completed between 2000 – 2015 by project mode
Notes: Australian transport projects completed between 2001 and 2015.
Source: Deloitte Investment Monitor dataset; Grattan analysis.
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\Results\Overall cost overruns

## Slide 15
Chart: 
| Expected value | Probability pricing | Sensitivity analysis | Reference class forecasting
Series 1 | 58.0645 | 45.1613 | 45.1613 | 19.3548
Notes: This chart has been reviewed on 21/10/2016.
Title: Australia’s various guidelines on risk measurement do not recommend any approach consistently.
Subtitle: Proportion of guidelines on quantitative risk assessment on transport infrastructure projects that recommend the use of each key risk assessment tool, per cent
Sources: Australian risk management guidelines referenced in appendix XX, and Deloitte Investment Monitor, Grattan analysis
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\Project appraisal process analysis\Project appraisal process

## Slide 16
50%
1
Underrun
Overrun
Expected value
P90
50%
40%
10%
Median = P50
Full distribution
Variance
Notes: This chart has been reviewed on 21/10/2016.
Title: Key risk measurement and management concepts
Subtitle: Illustrative probability distribution of cost outcomes on individual projects, per cent
Notes: The distribution of cost risks depicted is a stylized representation of the distribution of cost overruns observed in the Investment Monitor; see appendix xx for details. This graph’s illustrative purpose is to graphically present the relative distances between the median, 90th quantile and expected value of cost overruns.
Sources: Deloitte Investment Monitor, Grattan analysis

## Slide 17
Chart: 
| Contingency required for 90% confidence at the portfolio level | Contingency required for 90% confidence at the project level
Series 2 | 100 | 100
Series 1 | 70 | 24
Managed at the portfolio level
Managed at the project level
70%
24%
Notes: This chart has been reviewed on 21/10/2016.
Title: Small contingencies can achieve a lot when they are managed at the portfolio level
Subtitle: Value of the contingencies required to cover the costs of 90% of the cost overruns that occur after a formal budget commitment, under different contingency management schemes
Notes: Australian transport projects completed between 2000 and 2015
Sources: Deloitte Investment Monitor; Grattan analysis
Analysis in C:\Users\ldanks\Dropbox (Grattan Institute)\Transport Program\Project - Project-level Study\Analysis\Spreadsheets\Results\Summary statistics